## Table of Contents
TI Information - Selective Disclosure
Copyright (C) 2023 Texas Instruments Incorporated
Sheet No. | Title | Purpose
1 | Table of Contents | Provides an overview of the contents of the complete report.
2 | Script Input Parameters | Displays the input parameters provided to generate this report.
3 | Coverage Summary | Provides a summary report of Coverage for both Forward and Backward Traceability.
4 | Forward Traceability | Provides the detailed Forward Traceability Report from Marketing Requirements(MRD) to Software Product Specifications(SPS) & from Software Product Specifications(SPS) to Test Cases.
5 | Backward Traceability | Provides the detailed Backward Traceability Report from Software Product Specifications(SPS) to Marketing Requirements(MRD) & from Test Cases to Software Product Specifications(SPS).
6 | Traceability Deviations | Provides the details of all the Traceability Deviations.
7 | Revision History | Provides Template Revision History.

## Script Input Parameters
CM Record Key | Baseline Project Key | Report generated on
ISS-465 | ISS | 2023-08-14 13:56:49.508509-05:00 CDT

## Coverage Summary
Forward Coverage Type | Forward Percentage Covered | Backward Coverage Type | Backward Percentage Covered
Marketing Requirement (MRD) -> Software Product Specification (SPS) | 100.0% | Software Product Specification (SPS) -> Marketing Requirement (MRD) | 93.88%
Software Product Specification (SPS) -> Test Case | 87.76% | Test Case -> Software Product Specification (SPS) | 100.0%

## Forward Traceability
MRD ID | SPS ID(s) | SPS ID | Test Case ID(s) | Test Case Scope
JACINTOREQ-3493 | ISS-79,ISS-11,ISS-12 | ISS-79
JACINTOREQ-407 | ISS-79,ISS-80 | ISS-174 | ISS-187
JACINTOREQ-438 | ISS-174,ISS-133,ISS-25,ISS-132,ISS-155,ISS-16 | ISS-133 | ISS-111 | Unit
JACINTOREQ-304 | ISS-17,ISS-19,ISS-15,ISS-20,ISS-27,ISS-24,ISS-26,ISS-23,ISS-22,ISS-16 | ISS-17 | ISS-119 | Unit
JACINTOREQ-847 | ISS-157,ISS-158 | ISS-157 | ISS-139 | Integration
JACINTOREQ-1354 | ISS-217 | ISS-19 | ISS-118 | Unit
JACINTOREQ-5096 | ISS-217 | ISS-217 | ISS-231
JACINTOREQ-303 | ISS-9,ISS-11,ISS-10,ISS-12 | ISS-15 | ISS-120 | Unit
JACINTOREQ-56 | ISS-9,ISS-11,ISS-10,ISS-12,ISS-124 | ISS-20 | ISS-117 | Unit
JACINTOREQ-601 | ISS-211,ISS-129 | ISS-25 | ISS-67 | Unit
JACINTOREQ-1499 | ISS-223 | ISS-9 | ISS-90,ISS-83,ISS-88 | Integration,Unit,Unit
JACINTOREQ-832 | ISS-177,ADASVISION-4551,ISS-178,ISS-159 | ISS-211 | ISS-239
JACINTOREQ-1076 | ISS-213 | ISS-223 | ISS-112,ISS-90 | Unit,Integration
JACINTOREQ-3056 | ISS-129 | ISS-177 | ISS-49,ISS-72 | Integration,Integration
JACINTOREQ-516 | ISS-129 | ISS-213 | ISS-112 | Unit
JACINTOREQ-437 | ISS-92 | ISS-132 | ISS-164 | Unit
JACINTOREQ-1172 | ISS-208,ISS-207,ISS-202,ISS-206,ISS-204,ISS-203 | ISS-129 | ISS-239
JACINTOREQ-3497 | ISS-208 | ISS-155 | ISS-110 | Unit
JACINTOREQ-6272 | ISS-208,ISS-207,ISS-202,ISS-206,ISS-204,ISS-203 | ISS-80 | ISS-110 | Unit
JACINTOREQ-6268 | ISS-197,ISS-196 | ISS-92
JACINTOREQ-817 | ISS-197,ISS-196 | ISS-208 | ISS-242
JACINTOREQ-3499 | ISS-178 | ISS-207 | ISS-232
JACINTOREQ-111 | ISS-14 | ISS-11 | ISS-90 | Integration
JACINTOREQ-61 | ISS-14,ISS-12 | ISS-194
JACINTOREQ-1168 | ISS-214 | ISS-158 | ISS-112 | Unit
JACINTOREQ-2056 | ISS-212 | ISS-197 | ISS-216 | Unit
JACINTOREQ-1368 | ISS-236 | ADASVISION-4551 | ADASVISION-4342 | Unit
ISS-226 | ISS-203 | ISS-198
JACINTOREQ-2924 | ISS-124 | ISS-205
JACINTOREQ-396 | ISS-124 | ISS-202 | ISS-232
JACINTOREQ-539 | ISS-124 | ISS-178 | ISS-179
|  | ISS-14 | ISS-108,ISS-84,ISS-88,ISS-90 | Unit,Unit,Unit,Integration
|  | ISS-27 | ISS-113 | Unit
|  | ISS-196 | ISS-215,ADASVISION-4857 | Unit,Integration
|  | ISS-214 | ISS-139,ISS-112 | Integration,Unit
|  | ISS-24 | ISS-138
|  | ISS-26 | ISS-115 | Unit
|  | ISS-206 | ISS-232
|  | ISS-204 | ISS-242
|  | ISS-23 | ISS-116 | Unit
ISS-212
|  | ISS-159 | ISS-49,ISS-72 | Integration,Integration
|  | ISS-10 | ADASVISION-2460,ADASVISION-2461,ISS-108,ISS-65,ISS-73 | Integration,Integration,Unit,Integration,Integration
|  | ISS-236 | ISS-112 | Unit
|  | ISS-22 | ISS-141 | Integration
|  | ISS-16 | ISS-165 | Integration
|  | ISS-203 | ISS-237
|  | ISS-12 | ISS-88,ISS-49,ISS-112,ISS-90 | Unit,Integration,Unit,Integration
|  | ISS-124 | ISS-139 | Integration

## Backward Traceability
SPS ID | MRD ID(s) | Test Case ID | Test Case Scope | SPS ID(s)
ISS-79 | JACINTOREQ-3493,JACINTOREQ-407 | ISS-215 | Unit | ISS-196
ISS-174 | JACINTOREQ-438 | ISS-49 | Integration | ISS-61,ISS-159,ISS-177
ISS-133 | JACINTOREQ-438 | ISS-65 | Integration | ISS-10
ISS-17 | JACINTOREQ-304 | ISS-216 | Unit | ISS-197
ISS-157 | JACINTOREQ-847 | ISS-237 |  | ISS-203
ISS-19 | JACINTOREQ-304 | ISS-231 |  | ISS-217
ISS-217 | JACINTOREQ-1354,JACINTOREQ-5096 | ADASVISION-4342 | Unit | ADASVISION-4551
ISS-15 | JACINTOREQ-304 | ADASVISION-4857 | Integration | ISS-196
ISS-20 | JACINTOREQ-304 | ISS-164 | Unit | ISS-132
ISS-25 | JACINTOREQ-438 | ISS-165 | Integration | ISS-16
ISS-9 | JACINTOREQ-303,JACINTOREQ-56 | ISS-187 |  | ISS-174
ISS-211 | JACINTOREQ-601 | ISS-113 | Unit | ISS-27
ISS-223 | JACINTOREQ-1499 | ISS-115 | Unit | ISS-26
ISS-177 | JACINTOREQ-832 | ISS-116 | Unit | ISS-23
ISS-213 | JACINTOREQ-1076 | ISS-117 | Unit | ISS-20
ISS-132 | JACINTOREQ-438 | ISS-118 | Unit | ISS-19
ISS-129 | JACINTOREQ-3056,JACINTOREQ-516,JACINTOREQ-601 | ISS-119 | Unit | ISS-17
ISS-155 | JACINTOREQ-438 | ISS-120 | Unit | ISS-15
ISS-80 | JACINTOREQ-407 | ISS-232 |  | ISS-202,ISS-206,ISS-207
ISS-92 | JACINTOREQ-437 | ISS-112 | Unit | ISS-43,ISS-158,ISS-223,ISS-214,ISS-213,ISS-236
ISS-208 | JACINTOREQ-1172,JACINTOREQ-3497,JACINTOREQ-6272 | ISS-239 |  | ISS-211,ISS-129
ISS-207 | JACINTOREQ-1172,JACINTOREQ-6272 | ISS-108 | Unit | ISS-10,ISS-14
ISS-11 | JACINTOREQ-303,JACINTOREQ-3493,JACINTOREQ-56 | ISS-72 | Integration | ISS-94,ISS-177
ISS-194 |  | ISS-73 | Integration | ISS-45
ISS-158 | JACINTOREQ-847 | ISS-139 | Integration | ISS-124,ISS-157,ISS-214
ISS-197 | JACINTOREQ-6268,JACINTOREQ-817 | ISS-83 | Unit | ISS-103
ADASVISION-4551 | JACINTOREQ-832 | ISS-110 | Unit | ISS-80,ISS-155
ISS-198 |  | ISS-111 | Unit | ISS-77
ISS-205 |  | ISS-84 | Unit | ISS-45
ISS-202 | JACINTOREQ-1172,JACINTOREQ-6272 | ADASVISION-2460 | Integration | ISS-10
ISS-178 | JACINTOREQ-3499,JACINTOREQ-832 | ADASVISION-2461 | Integration | ADASVISION-1865
ISS-14 | JACINTOREQ-111,JACINTOREQ-61 | ISS-90 | Integration | ISS-9,ISS-11,ISS-12,ISS-14,ISS-223
ISS-27 | JACINTOREQ-304 | ISS-138 |  | ISS-24
ISS-196 | JACINTOREQ-6268,JACINTOREQ-817 | ISS-141 | Integration | ISS-21
ISS-214 | JACINTOREQ-1168 | ISS-242 |  | ISS-208,ISS-204
ISS-24 | JACINTOREQ-304 | ISS-67 | Unit | ISS-62
ISS-26 | JACINTOREQ-304 | ISS-88 | Unit | ISS-46,ISS-12,ISS-14
ISS-206 | JACINTOREQ-1172,JACINTOREQ-6272 | ISS-179 |  | ISS-178
ISS-204 | JACINTOREQ-1172,JACINTOREQ-6272
ISS-23 | JACINTOREQ-304
ISS-212 | JACINTOREQ-2056
ISS-159 | JACINTOREQ-832
ISS-10 | JACINTOREQ-303,JACINTOREQ-56
ISS-236 | JACINTOREQ-1368
ISS-22 | JACINTOREQ-304
ISS-16 | JACINTOREQ-304,JACINTOREQ-438
ISS-203 | ISS-226,JACINTOREQ-1172,JACINTOREQ-6272
ISS-12 | JACINTOREQ-303,JACINTOREQ-3493,JACINTOREQ-56,JACINTOREQ-61
ISS-124 | JACINTOREQ-2924,JACINTOREQ-396,JACINTOREQ-539,JACINTOREQ-56

## Traceability Deviations
Coverage Type | Parameter ID(s) | Justification for Traceability Deviation
Software Product Specification (SPS) -> Test Case | ISS-79 | Tested ISS-110 for this but link is missing
Software Product Specification (SPS) -> Test Case | ISS-92 | MR JACINTOREQ-437 Implemented and FR ISS-92 Rejected
Software Product Specification (SPS) -> Test Case | ISS-194 | MR JACINTOREQ-1076 Implemented and FR ISS-194 Rejected
Software Product Specification (SPS) -> Test Case | ISS-198 | No MR and FR ISS-198 Rejected
Software Product Specification (SPS) -> Test Case | ISS-205 | MR JACINTOREQ-1172 Implemented and FR ISS-205 Deferred
Software Product Specification (SPS) -> Test Case | ISS-212 | MR JACINTOREQ-601 Implemented and FR ISS-212 Deferred
Software Product Specification (SPS) -> Marketing Requirement (MRD) | ISS-194 | MR JACINTOREQ-1076 Implemented and FR ISS-194 Rejected
Software Product Specification (SPS) -> Marketing Requirement (MRD) | ISS-198 | No MR and FR ISS-198 Rejected
Software Product Specification (SPS) -> Marketing Requirement (MRD) | ISS-205 | MR JACINTOREQ-1172 Implemented and FR ISS-205 Deferred

## Template Revision History
Author | Version | Date | Description
Krishna/ Dhruv | A | 20/1/2023 | Initial version