## Summary
TI Confidential - NDA Restrictions
Copyright © 2018 Texas Instruments Incorporated. All rights reserved.
Information in this document is subject to change without notice. Texas Instruments may have pending patent applications, trademarks, copyrights, or other intellectual property rights covering matter in this document. The furnishing of this documents is given for usage with Texas Instruments products only and does not give you any license to the intellectual property that might be contained within this document. Texas Instruments makes no implied or expressed warranties in this document and is not responsible for the products based from this document.
WDG Test Plan
Release | MCAL_AM62X_02.01.00_ENG_REL
Date | 2023-03-06
Platform | AM62X
Tester Name | Raja Kumar
Required Baseline Version | MCAL_AM62X_AM62Q_02.01.00
Scope | MPU
Requirement Summary
Total Designs | 94
Implemented | 94
Tested | 94
Testcase Pending | 0
Design Coverage | 100%
Testcase Scope Summary
Unit | 31
Integration | 34
Qualification | 11
Design to Test Coverage
Test Result
Module | Total Designs | Implemented | Pending | Coverage | PASS | FAIL | NI
WDG | 94 | 94 | 0 | 100% | 76 | 0 | 0

## WDG_Test_Matrix
WDG Test Matrix
Test Summary
|  | Total Test Cases |  | 76
|  | PASS |  | 76
|  | FAIL |  | 0
|  | NI |  | 0
Method of Tests
S.No | JIRA ID | ID | Test Scope | Requirement Mapping | Description | Expected Output | Verification Method | Priority | Test Result | Requirement | Interface | Fault | Resource | Method of deriving | Test Adequacy
1 | MCAL-2899 | 1 | Unit | :MCAL-5599:MCAL-5558:MCAL-5603:MCAL-5560:MCAL-5603:MCAL-5623:MCAL-5543:MCAL-5594:MCAL-5569:MCAL-5612:MCAL-5551:MCAL-5622:MCAL-5547:MCAL-5557:MCAL-5587:MCAL-5584:MCAL-5542:MCAL-5621:MCAL-5586:MCAL-5550:MCAL-5618:MCAL-5592:MCAL-5593:MCAL-5590:MCAL-5571:MCAL-5616:MCAL-5578:MCAL-5624:MCAL-5604:MCAL-5597: | WDG 1 Sec Test - FAST MODE MCU RTI Instance 0, 12.5 MHz FCLK | WDG should be serviced by the driver with set trigger condition(until trigger counter = 0) and then it should generate an interrupt to ESM after expiry. Confirm interrupt generated to ESM is from WDG only. | EVM Verification | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
2 | MCAL-2899 | 1 | Integration | MCAL-5584 | WDG Module: Test case to check initialized the WDG driver. To test API functionality(Wdg_init()) | Should not report DET error and extended error accordingly | EVM Verification | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
3 | MCAL-2899 | 1 | Integration | MCAL-5567 | WDG module: Sets the timeout value for the trigger counter. To test API functionality(Wdg_SetTriggerCondition()) | Should not report DET error accordingly | EVM Verification | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
4 | MCAL-2899 | 1 | Integration | MCAL-5595 | WDG module: trigger Routine Test. To test API functionality(Wdg_Trigger()) | Should not report DET error accordingly | EVM Verification | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
5 | MCAL-2900 | 2 | Unit | :MCAL-5599:MCAL-5558:MCAL-5603:MCAL-5560:MCAL-5603:MCAL-5623:MCAL-5543:MCAL-5594:MCAL-5569:MCAL-5612:MCAL-5551:MCAL-5622:MCAL-5547:MCAL-5557:MCAL-5587:MCAL-5584:MCAL-5542:MCAL-5621:MCAL-5586:MCAL-5550:MCAL-5618:MCAL-5592:MCAL-5593:MCAL-5590:MCAL-5571:MCAL-5616:MCAL-5578:MCAL-5624:MCAL-5604:MCAL-5597: | WDG 2 Sec Test - SLOW MODE MCU RTI Instance 0, 12.5 MHz FCLK | WDG should be serviced by the driver with set trigger condition(until trigger counter = 0) and then it should generate an interrupt to ESM after expiry. Confirm interrupt generated to ESM is from WDG only. | EVM Verification | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
6 | MCAL-2901 | 3 | Unit | :MCAL-5577: | WDG START TIME VIOLATION TEST 50% WINDOW SIZE MCU RTI Instance 0, 12.5 MHz FCLK | WDG should be serviced by the driver with set trigger condition(until trigger counter = 0) and then it should generate an interrupt to ESM immediately. Confirm interrupt generated to ESM is from WDG only. | EVM Verification | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
7 | MCAL-2902 | 4 | Integration | :MCAL-5576: | WDG Module ID and Version Info Test | It should print expected Module Id (102) and version info correctly | EVM Verification | P0 | PASS | √ | √ |  |  | Error guessing | Functional
8 | MCAL-2903 | 5 | Unit | :MCAL-5553:MCAL-5619: | WDG Register ReadBack Test MCU RTI Instance 0, 12.5 MHZ FCLK | WDG should be serviced by the driver with set trigger condition(until trigger counter = 0) and then it should generate an interrupt to ESM immediately. Confirm interrupt generated to ESM is from WDG only. Register contents captured after Init and during serviving watchdog should be same if Readback API is called in between. | EVM Verification | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
9 | MCAL-2903 | 5 | Integration | :MCAL-5893: | WDG Module: Safety Diagnostic Features functionality test case | Safety Diagnostic Features work as expected without reporting errors. Internal Diagnostic mode can be Enabled and Disabled. Critical Registers can be read successfully. Anything else, like error prints (ERROR / Error / error) and/or DET/DEM, notifications & hang indicates a failure. | EVM Verification | P0 | PASS | √ | √ |  |  | Failure Mode Analysis | Functional
10 | MCAL-2904 | 101 | Unit | :MCAL-5599:MCAL-5558:MCAL-5603:MCAL-5560:MCAL-5603:MCAL-5623:MCAL-5543:MCAL-5594:MCAL-5569:MCAL-5612:MCAL-5551:MCAL-5622:MCAL-5547:MCAL-5557:MCAL-5587:MCAL-5584:MCAL-5542:MCAL-5621:MCAL-5586:MCAL-5550:MCAL-5618:MCAL-5592:MCAL-5593:MCAL-5590:MCAL-5571:MCAL-5616:MCAL-5578:MCAL-5624:MCAL-5604:MCAL-5597: | WDG Test - FAST MODE MIN TimeOut Value(WDG Set Trigger Condition Immediate Reset) MCU RTI Instance 0, 12.5 MHZ FCLK | WDG Set Trigger condition should generate an interrupt to ESM immediately.Confirm interrupt generated to ESM is from WDG only. | EVM Verification | P0 | PASS | √ | √ |  |  | Generation and analysis of equivalence classes | Functional
11 | MCAL-2904 | 101 | Integration | MCAL-5607 | Test case to check The WDG module Internal Wdg Req : Access | Ensure WDG module To access the internal watchdog hardware, the corresponding Wdg module instance shall access the hardware for watchdog servicing directly | EVM Verification | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
12 | MCAL-2905 | 102 | Unit | :MCAL-5599:MCAL-5558:MCAL-5603:MCAL-5560:MCAL-5603:MCAL-5623:MCAL-5543:MCAL-5594:MCAL-5569:MCAL-5612:MCAL-5551:MCAL-5622:MCAL-5547:MCAL-5557:MCAL-5587:MCAL-5584:MCAL-5542:MCAL-5621:MCAL-5586:MCAL-5550:MCAL-5618:MCAL-5592:MCAL-5593:MCAL-5590:MCAL-5571:MCAL-5616:MCAL-5578:MCAL-5624:MCAL-5604:MCAL-5597: | WDG Test, FAST MODE, (MIN + MAX / 2) TIMEOUT Value (WDG Set Trigger Condition ~32 Seconds) MCU RTI Instance 0, 12.5 MHZ FCLK | WDG should be serviced by the driver with set trigger condition(until trigger counter = 0) and then it should generate an interrupt to ESM after expiry. Confirm interrupt generated to ESM is from WDG only. | EVM Verification | P0 | PASS | √ | √ |  |  | Generation and analysis of equivalence classes | Functional
13 | MCAL-2906 | 103 | Unit | :MCAL-5599:MCAL-5558:MCAL-5603:MCAL-5560:MCAL-5603:MCAL-5623:MCAL-5543:MCAL-5594:MCAL-5569:MCAL-5612:MCAL-5551:MCAL-5622:MCAL-5547:MCAL-5557:MCAL-5587:MCAL-5584:MCAL-5542:MCAL-5621:MCAL-5586:MCAL-5550:MCAL-5618:MCAL-5592:MCAL-5593:MCAL-5590:MCAL-5571:MCAL-5616:MCAL-5578:MCAL-5624:MCAL-5604:MCAL-5597: | WDG Test, FAST MODE, MAX TIMEOUT Value (WDG Set Trigger Condition 65 Seconds) MCU RTI Instance 0, 12.5 MHZ FCLK | WDG should be serviced by the driver with set trigger condition(until trigger counter = 0) and then it should generate an interrupt to ESM after expiry. Confirm interrupt generated to ESM is from WDG only. | EVM Verification | P0 | PASS | √ | √ |  |  | Generation and analysis of equivalence classes | Functional
14 | MCAL-2907 | 104 | Unit | :MCAL-5599:MCAL-5558:MCAL-5603:MCAL-5560:MCAL-5603:MCAL-5623:MCAL-5543:MCAL-5594:MCAL-5569:MCAL-5612:MCAL-5551:MCAL-5622:MCAL-5547:MCAL-5557:MCAL-5587:MCAL-5584:MCAL-5542:MCAL-5621:MCAL-5586:MCAL-5550:MCAL-5618:MCAL-5592:MCAL-5593:MCAL-5590:MCAL-5571:MCAL-5616:MCAL-5578:MCAL-5624:MCAL-5604:MCAL-5597: | WDG 500 mSec Test - FAST MODE MCU RTI Instance 1, 12.5 MHZ FCLK | WDG should be serviced by the driver with set trigger condition(until trigger counter = 0) and then it should generate an interrupt to ESM after expiry. Confirm interrupt generated to ESM is from WDG only. | EVM Verification | P0 | PASS | √ | √ |  |  | Generation and analysis of equivalence classes | Functional
15 | MCAL-2908 | 105 | Unit | :MCAL-5599:MCAL-5558:MCAL-5603:MCAL-5560:MCAL-5603:MCAL-5623:MCAL-5543:MCAL-5594:MCAL-5569:MCAL-5612:MCAL-5551:MCAL-5622:MCAL-5547:MCAL-5557:MCAL-5587:MCAL-5584:MCAL-5542:MCAL-5621:MCAL-5586:MCAL-5550:MCAL-5618:MCAL-5592:MCAL-5593:MCAL-5590:MCAL-5571:MCAL-5616:MCAL-5578:MCAL-5624:MCAL-5604:MCAL-5597: | WDG 250 mSec Test - FAST MODE MCU RTI Instance 1, 12.5 MHZ FCLK | WDG should be serviced by the driver with set trigger condition(until trigger counter = 0) and then it should generate an interrupt to ESM after expiry. Confirm interrupt generated to ESM is from WDG only. | EVM Verification | P0 | PASS | √ | √ |  |  | Generation and analysis of equivalence classes | Functional
16 | MCAL-2909 | 106 | Unit | :MCAL-5599:MCAL-5558:MCAL-5603:MCAL-5560:MCAL-5603:MCAL-5623:MCAL-5543:MCAL-5594:MCAL-5569:MCAL-5612:MCAL-5551:MCAL-5622:MCAL-5547:MCAL-5557:MCAL-5587:MCAL-5584:MCAL-5542:MCAL-5621:MCAL-5586:MCAL-5550:MCAL-5618:MCAL-5592:MCAL-5593:MCAL-5590:MCAL-5571:MCAL-5616:MCAL-5578:MCAL-5624:MCAL-5604:MCAL-5597: | WDG 750 mSec Test - FAST MODE MCU RTI Instance 1, 12.5 MHZ FCLK | WDG should be serviced by the driver with set trigger condition(until trigger counter = 0) and then it should generate an interrupt to ESM after expiry. Confirm interrupt generated to ESM is from WDG only. | EVM Verification | P0 | PASS | √ | √ |  |  | Generation and analysis of equivalence classes | Functional
17 | MCAL-2910 | 107 | Unit | :MCAL-5599:MCAL-5558:MCAL-5603:MCAL-5560:MCAL-5603:MCAL-5623:MCAL-5543:MCAL-5594:MCAL-5569:MCAL-5612:MCAL-5551:MCAL-5622:MCAL-5547:MCAL-5557:MCAL-5587:MCAL-5584:MCAL-5542:MCAL-5621:MCAL-5586:MCAL-5550:MCAL-5618:MCAL-5592:MCAL-5593:MCAL-5590:MCAL-5571:MCAL-5616:MCAL-5578:MCAL-5624:MCAL-5604:MCAL-5597: | WDG 1 mSec Test - FAST MODE MCU RTI Instance 1, 12.5 MHZ FCLK, Equivalence partition test | WDG should be serviced by the driver with set trigger condition(until trigger counter = 0) and then it should generate an interrupt to ESM after expiry. Confirm interrupt generated to ESM is from WDG only. | EVM Verification | P0 | PASS | √ | √ |  |  | Generation and analysis of equivalence classes | Functional
18 | MCAL-2911 | 108 | Unit | :MCAL-5599:MCAL-5558:MCAL-5603:MCAL-5560:MCAL-5603:MCAL-5623:MCAL-5543:MCAL-5594:MCAL-5569:MCAL-5612:MCAL-5551:MCAL-5622:MCAL-5547:MCAL-5557:MCAL-5587:MCAL-5584:MCAL-5542:MCAL-5621:MCAL-5586:MCAL-5550:MCAL-5618:MCAL-5592:MCAL-5593:MCAL-5590:MCAL-5571:MCAL-5616:MCAL-5578:MCAL-5624:MCAL-5604:MCAL-5597: | WDG 2500 mSec Test - SLOW MODE MCU RTI Instance 1, 12.5 MHZ FCLK, Equivalence partition test | WDG should be serviced by the driver with set trigger condition(until trigger counter = 0) and then it should generate an interrupt to ESM after expiry. Confirm interrupt generated to ESM is from WDG only. | EVM Verification | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
19 | MCAL-2912 | 201 | Unit | :MCAL-5577: | WDG 1 Sec Test, FAST MODE, 50 percent WINDOW SIZE, END TIME VIOLATION TEST, MCU RTI Instance 0, 12.5 MHZ FCLK | WDG should be serviced by the driver with set trigger condition(until trigger counter = 0) and then it should generate an interrupt to ESM after expiry. Confirm interrupt generated to ESM is from WDG only. | EVM Verification | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
20 | MCAL-2913 | 202 | Unit | :MCAL-5577: | WDG 2 Sec Test, SLOW MODE, 25 percent WINDOW SIZE, END TIME VIOLATION TEST, MCU RTI Instance 0, 12.5 MHZ FCLK | WDG should be serviced by the driver with set trigger condition(until trigger counter = 0) and then it should generate an interrupt to ESM after expiry. Confirm interrupt generated to ESM is from WDG only. | EVM Verification | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
21 | MCAL-2914 | 203 | Unit | :MCAL-5577: | WDG 1 Sec Test, FAST MODE, 12.5 percent WINDOW SIZE, END TIME VIOLATION TEST, MCU RTI Instance 0, 12.5 MHZ FCLK | WDG should be serviced by the driver with set trigger condition(until trigger counter = 0) and then it should generate an interrupt to ESM after expiry. Confirm interrupt generated to ESM is from WDG only. | EVM Verification | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
22 | MCAL-2915 | 204 | Unit | :MCAL-5577: | WDG 2 Sec Test, SLOW MODE, 6.25 percent WINDOW SIZE, END TIME VIOLATION TEST, MCU RTI Instance 0, 12.5 MHZ FCLK | WDG should be serviced by the driver with set trigger condition(until trigger counter = 0) and then it should generate an interrupt to ESM after expiry. Confirm interrupt generated to ESM is from WDG only. | EVM Verification | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
23 | MCAL-2916 | 205 | Unit | :MCAL-5577: | WDG 1 Sec Test, FAST MODE, 3.125 percent WINDOW SIZE, END TIME VIOLATION TEST, MCU RTI Instance 0, 12.5 MHZ FCLK | WDG should be serviced by the driver with set trigger condition(until trigger counter = 0) and then it should generate an interrupt to ESM after expiry. Confirm interrupt generated to ESM is from WDG only. | EVM Verification | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
24 | MCAL-2927 | 301 | Unit | :MCAL-5599:MCAL-5558:MCAL-5603:MCAL-5560:MCAL-5603:MCAL-5623:MCAL-5543:MCAL-5594:MCAL-5569:MCAL-5612:MCAL-5551:MCAL-5622:MCAL-5547:MCAL-5557:MCAL-5587:MCAL-5584:MCAL-5542:MCAL-5621:MCAL-5586:MCAL-5550:MCAL-5618:MCAL-5592:MCAL-5593:MCAL-5590:MCAL-5571:MCAL-5616:MCAL-5578:MCAL-5624:MCAL-5604:MCAL-5597: | WDG 1 Sec Test - FAST MODE MCU RTI Instance 0, HFOSC0_CLKOUT FCLK | WDG should be serviced by the driver with set trigger condition(until trigger counter = 0) and then it should generate an interrupt to ESM after expiry. Confirm interrupt generated to ESM is from WDG only. | EVM Verification | P1 | PASS | √ | √ |  |  | Requirements Analysis | Functional
25 | MCAL-2928 | 302 | Unit | :MCAL-5599:MCAL-5558:MCAL-5603:MCAL-5560:MCAL-5603:MCAL-5623:MCAL-5543:MCAL-5594:MCAL-5569:MCAL-5612:MCAL-5551:MCAL-5622:MCAL-5547:MCAL-5557:MCAL-5587:MCAL-5584:MCAL-5542:MCAL-5621:MCAL-5586:MCAL-5550:MCAL-5618:MCAL-5592:MCAL-5593:MCAL-5590:MCAL-5571:MCAL-5616:MCAL-5578:MCAL-5624:MCAL-5604:MCAL-5597: | WDG 1 Sec Test - FAST MODE MCU RTI Instance 0, LFOSC_CLKOUT FCLK | WDG should be serviced by the driver with set trigger condition(until trigger counter = 0) and then it should generate an interrupt to ESM after expiry. Confirm interrupt generated to ESM is from WDG only. | EVM Verification | P1 | PASS | √ | √ |  |  | Requirements Analysis | Functional
26 | MCAL-2924 | 303 | Unit | :MCAL-5599:MCAL-5558:MCAL-5603:MCAL-5560:MCAL-5603:MCAL-5623:MCAL-5543:MCAL-5594:MCAL-5569:MCAL-5612:MCAL-5551:MCAL-5622:MCAL-5547:MCAL-5557:MCAL-5587:MCAL-5584:MCAL-5542:MCAL-5621:MCAL-5586:MCAL-5550:MCAL-5618:MCAL-5592:MCAL-5593:MCAL-5590:MCAL-5571:MCAL-5616:MCAL-5578:MCAL-5624:MCAL-5604:MCAL-5597: | WDG 1 Sec Test - FAST MODE MCU RTI Instance 0,32 KHz FCLK, Run with Config 3 | WDG should be serviced by the driver with set trigger condition(until trigger counter = 0) and then it should generate an interrupt to ESM after expiry. Confirm interrupt generated to ESM is from WDG only. | EVM Verification | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
27 | MCAL-2917 | 501 | Unit | :MCAL-5579:MCAL-5572:MCAL-5591:MCAL-5580:MCAL-5544:MCAL-5563:MCAL-5620:MCAL-5548:MCAL-5625: | WDG_Init Development Error Detection and Extended Production Error Test.WDG_Init with default mode (WDGIF_OFF_MODE) | Should report DET error and extended error accordingly | EVM Verification | P0 | PASS | √ | √ |  |  | Boundary Value Analysis | Fault Injection
28 | MCAL-2917 | 501 | Integration | MCAL-5632 | Test case to check The WDG Driver Shall allow development errors, and extended production errors | Should report DET error and extended error accordingly | EVM Verification | P0 | PASS | √ | √ |  |  | Boundary Value Analysis | Functional
29 | MCAL-2917 | 501 | Integration | MCAL-5583 | Test case to check The WDG Driver SWS_Wdg_00111 Dem_SetEventStatus and Set_REportError services shall be used. | Should report DET error and extended error accordingly | EVM Verification | P0 | PASS | √ | √ |  |  | Boundary Value Analysis | Functional
30 | MCAL-2918 | 502 | Unit | :MCAL-5555: | Wdg_SetTriggerCondition Development Error Detection Test | Should report DET error accordingly | EVM Verification | P0 | PASS | √ | √ |  |  | Boundary Value Analysis | Fault Injection
31 | MCAL-2919 | 503 | Unit | :MCAL-5575: | Wdg_GetVersionInfo Development Error Detection Test | Should report DET error accordingly | EVM Verification | P0 | PASS | √ | √ |  |  | Boundary Value Analysis | Fault Injection
32 | MCAL-2920 | 504 | Unit | :MCAL-5614:MCAL-5598: | Wdg_Trigger Development Error Detection Test | Should report DET error accordingly | EVM Verification | P0 | PASS | √ | √ |  |  | Boundary Value Analysis | Fault Injection
33 | MCAL-2921 | 505 | Unit | :MCAL-5579: | WDG Get Base Addr API Development Error Detection Test - (for coverage purpose) | Should report DET error and extended error accordingly | EVM Verification | P0 | PASS | √ | √ |  |  | Boundary Value Analysis | Fault Injection
34 | MCAL-2922 | 506 | unit | :MCAL-5553: | Wdg_RegisterReadBack Development Error Detection Test | Should report error accordingly | EVM Verification | P0 | PASS | √ | √ |  |  | Boundary Value Analysis | Fault Injection
35 | MCAL-7718 | 507 | Unit | MCAL-5577 | Wdg_WindowConfig Development Error Detection Test | Should report error accordingly | EVM Verification | P0 | PASS | √ | √ |  |  | Boundary Value Analysis | Fault Injection
36 | MCAL-7721 | 508 | Unit |  | Wdg_SetMode Test | wdg_SetMode test(for dynamic coverage purpose-Dummy Function, just to return E_OK if called from WDG IF layer) | EVM Verification | P0 | PASS | √ | √ |  |  | Boundary Value Analysis | Fault Injection
37 | MCAL-2923 | 1001 | Unit | :MCAL-5599:MCAL-5558:MCAL-5603:MCAL-5560:MCAL-5603:MCAL-5623:MCAL-5543:MCAL-5594:MCAL-5569:MCAL-5612:MCAL-5551:MCAL-5622:MCAL-5547:MCAL-5557:MCAL-5587:MCAL-5584:MCAL-5542:MCAL-5621:MCAL-5586:MCAL-5550:MCAL-5618:MCAL-5592:MCAL-5593:MCAL-5590:MCAL-5571:MCAL-5616:MCAL-5578:MCAL-5624:MCAL-5604:MCAL-5597: | WDG 1 Sec Test - FAST MODE MCU RTI Instance 0, Generate Signal from RTI(ESM Interrupt) 12.5 MHz FCLK | ESM should generate pulse and should be observed on Error Pin. | EVM Verification | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
38 | MCAL-2923 | 1001 | Integration | MCAL-5554 | Wdg module depends on the external module ESM to generate pulse after expiry which could be used to trigger SoC reset | ESM should generate pulse and should be observed on Error Pin...Anything else, like error prints (ERROR / Error / error) and/or DET/DEM, notifications & hang indicates a failure | EVM Verification | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
39 | MCAL-2926 | 5001 | Unit | MCAL-5559: | Dummy test case for capturing requirements which needs to be verified | Verification Required. Check the Verification sheets | Code Review | P1 | PASS | √ | √ |  |  | Requirements Analysis | Verification
40 | MCAL-3052 | 3001 | unit | :MCAL-5626:MCAL-5617:MCAL-5602:MCAL-5585:MCAL-5613:MCAL-5589:MCAL-5556: MCAL-5552:MCAL-5608:MCAL-5566:MCAL-5610:MCAL-5615:MCAL-5605:MCAL-5574:MCAL-5588: MCAL-5561:MCAL-5601:MCAL-5600:MCAL-5565:MCAL-5562:MCAL-5581:MCAL-5599:MCAL-5541:MCAL-5570:MCAL-5582:MCAL-5606:MCAL-5609:MCAL-5611: | Wdg Configurator ECUC requirements review | Should generate valid configuration for PC, LT and PB variants | EVM Verification | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
41 | MCAL-2925 | 4001 | Integration | :MCAL-5568:MCAL-5564: | Resource usage test : Stack size, Code size | Verify the WDG driver should meet the requirements MCAL-5568,MCAL-5564. Anything else, like error prints (ERROR / Error / error) and/or DET/DEM, notifications & hang indicates a failure. | EVM Verification | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
42 | MCAL-7752 | 4002 | Integration | MCAL-5573 | WDG Module: File Structure | Verify WDG module file include structure is as per MCAL-5573 | Code Review | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
43 | MCAL-7753 | 4003 | Integration | MCAL-5894 | WDG Module shall follow General Design Rules as listed by AUTOSAR Spec 4.3.1 section 7.1. | verify WDG Driver follows General Design Rules as listed by AUTOSAR Spec 4.3.1 section 7.1 | Document review | P0 | PASS | √ | √ |  |  | Requirements Analysis | usability
44 | MCAL-7769 | 4004 | Integration | MCAL-5631 | Test case to check The WDG Driver shall have Imported types from following modules: Dem, Std_Types and WdgIf. Refer to SWS_Wdg_00105. It shall also define a new type for "Wdg_ConfigType", refer to SWS_Wdg_00171 | Verify and ensure that WDG driver imported types from Dem, Std_Types and WdgIf. | code Review | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
45 | MCAL-7754 | 4005 | Integration | MCAL-5630 | WDG Module shall follow the sequence diagram as described in Autosar Spec | WDG module follows the sequence diagram as described in Autosar Spec. | code Review | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
46 | MCAL-3030 | 4006 | Integration | MCAL-7688 | WDG Common :The MCAL shall support EB Tresos Configurator for configuration of MCAL modules. | Verify MCAL-921 is implemented and ensure the configuration is generated using Tresos EB GUI |  | P0 | PASS | √ | √ |  |  | Requirements Analysis | Interface
47 | MCAL-3031 | 4007 | Integration | MCAL-7689 | MCAL modules shall be able to build and execute in Release Profile | Verify daily/rc build log. There should no error / warings and binary generated. | Code Review | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
48 | MCAL-3032 | 4008 | Integration | MCAL-7695 | WDG Module Common: MCAL modules shall be able to build and execute in Debug Profile | Verify daily/rc build log. There should no error / warings and binary generated. | Code Review | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
49 | MCAL-3033 | 4009 | Integration | MCAL-7684 | WDG Module Common: The MCAL shall be licensed under TI Commercial using SRAS process | Verify installer .mpi (provide path) has SRAS license | Review | P0 | PASS | √ | √ |  |  | Requirements Analysis | usability
50 | MCAL-3034 | 4010 | Integration | MCAL-7693 | WDG Module Common: The MCAL modules shall support C++ build (i.e. only the MCAL libraries shall support c++ build) | Verify daily/rc build log. There should no error / warings. | Review | P0 | PASS | √ | √ |  |  | Requirements Analysis | Interface
51 | MCAL-3035 | 4011 | Integration | MCAL-7685 | WDG Module Common: The MCAL package shall include release notes. In addition previous Release Notes documents shall also be archived and provided in each release package | Check for release notes in included in RC package at mcusw_xx_yy_zz_bb/docs/ | Review | P0 | PASS | √ | √ |  |  | Requirements Analysis | usability
52 | MCAL-3038 | 4012 | Integration | MCAL-7680 | WDG Module Common: The build mechanism shall provide ability to build individual MCAL modules. This is required to ensure customer could selectively use MCAL modules with AUTOSAR stack | WDG Module Common: The build mechanism shall provide ability to build individual MCAL modules. This is required to ensure customer could selectively use MCAL modules with AUTOSAR stack | Review | P0 | PASS | √ | √ |  |  | Requirements Analysis | Interface
53 | MCAL-3042 | 4013 | Integration | MCAL-7696 | WDG Module Common: The MCAL shall not do any dynamic allocation of memory. All memory requirement should be statically allocated at compile time | Ensure PDK/CSL OS allocation API's are not used. Hint grep for API names such as malloc,calloc are called in drivers. | Review | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
54 | MCAL-3043 | 4014 | Integration | MCAL-7682 | WDG Module Common: All MCAL modules shall document the detailed design of the module. | Verify the generated doxygen API documentation. | Review | P0 | PASS | √ | √ |  |  | Requirements Analysis | usability
55 | MCAL-3045 | 4015 | Integration | MCAL-7679 | WDG Module Common: Source installer shall contain only source files | Common for all modules, check if the installer installs only source | Review | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
56 | MCAL-3046 | 4016 | Integration | MCAL-7690 | WDG Module Common: The MCAL shall support Makefile based build | Common for all modules, check user guide for non-make based build mechanisims. | Review | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
57 | MCAL-3047 | 4017 | Integration | MCAL-7677 | WDG Module Common: The MCAL shall provide User Guide documentation with details on installation and out-of-box instructions, driver details, feature information and programming information.As prescribed by SWS_BSW_00002 of AUTOSAR_SWS_BSWGeneral.pdf | Verify the generated doxygen API documentation and check module user guide review pages | Document review | P0 | PASS | √ | √ |  |  | Requirements Analysis | usability
58 | MCAL-3050 | 4018 | Integration | MCAL-7681 | WDG Module Common: MCUSW demo application and driver demo applications requires to register ISR to interrupts, MCUSW shall depend on PDK utilities for interrupt registration and display result/status on console via print utilities | Code review : check if PDK OSAL API's are used for registation of interrupts. | Code Review | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
59 | MCAL-3051 | 4019 | Integration | MCAL-7676 | WDG Module Common: MCUSW driver and demo application will depend on UDMA to move data from & to peripheral to & from memory. MCUSW shall depend on PDK to provide UDMA libraries that could be used to program UDMA for data movement | Code review : Ensure the module makefile dosen't include UDMA as a dependent component. | Code Review | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
60 | MCAL-3065 | 4020 | Integration | MCAL-7698 | WDG Module Common: A separate configurator installer shall be provided. | Check if a separate installer mcusw_xx_yy_zz_bb_config.exe is provided in the RC build. | Review | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
61 | MCAL-3066 | 4021 | Integration | MCAL-7678 | WDG Module Common: The MCAL modules shall not access any memory or any common peripheral/registers other than the module memory space. | Verified through code review, check module code review comments/status | Code Review | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
62 | MCAL-3044 | 4022 | Integration | MCAL-7692 | WDG Module Common: The MCAL package shall include appropriate license & manifest documents approved by marketing & legal | Verify installer .mpi (provide path) has SRAS license | Review | P0 | PASS | √ | √ |  |  | Requirements Analysis | usability
63 | MCAL-3040 | 4023 | Integration | MCAL-7687 | WDG Common: MCAL source shall be installable on Linux and Windows desktop. The deliverable will be an installer for Linux and Windows. The configurator package shall be installable on windows platform only (as EB is not supported on Linux) | Common for all modules, check if the installer install mcusw on a linux and windows m/c | Review | P0 | PASS | √ | √ |  |  | Requirements Analysis | usability
64 | MCAL-3041 | 4024 | Integration | MCAL-7677 | WDG Module Common: The user-interface level sources shall be documented using Doxygen style.For the APIs that are exposed to user, the function comments shall be more detailed. For example the function shall contain details on the parameter, example, return values etc | Verify the generated doxygen API documentation. | Review | P0 | PASS | √ | √ |  |  | Requirements Analysis | usability
65 | MCAL-7956 | 4025 | Integration | :MCAL-5568:MCAL-5564: | WDG Common: Memory Corruption Test. | Verify that there is no corruption in stack and memory section. | EVM Verification | P0 | PASS |  |  |  | √ | Requirements Analysis | Stress
66 | MCAL-7799 | 6001 | Qualification | MCAL-5629 | MCAL shall provide a User guide and Design document for WDG module. | Verify and check WDG module user guide and design document for WDG functionality | Document review | P0 | PASS | √ | √ |  |  | Requirements Analysis | usability
67 | MCAL-7770 | 6002 | Qualification | MCAL-5628 | WDG module shall use RTI Hardware IP on J7ES and implement External Watchdog. | Verify WDG module uses RTI Hardware IP on J7ES. | Code Review | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
68 | MCAL-7755 | 6003 | Qualification | MCAL-5549 | MCAL Module: WDG: ASIL D Process | Ensure WDG driver implemented as per ASIL D process | Code Review | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
69 | MCAL-7756 | 6004 | Qualification | MCAL-5545 | WDG Module Common: The MCAL WDG module is developed based on AUTOSAR 4.3.1 specification | Verify MCAL-5546 is implemented. Verify the Configuration are correct as per AUTOSAR 4.3.1 specification. | Vector Tool | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
70 | MCAL-7757 | 6005 | Qualification | MCAL-5546 | WDG Module: MCAL WDG module supports AUTOSAR 4.3.1 API | Verify WDG functionality works as expected without errors. | EVM Verification | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
71 | MCAL-7759 | 6006 | Qualification | MCAL-5596 | WDG Module: MCAL Module: WDG: CSL Library Porting | Verify and ensure the CSL files are present within WDG MCAL module and WDG MCAL module is independent of PDK CSL library | Code Review | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
72 | MCAL-7771 | 6007 | Qualification | MCAL-7686 | WDG Module: MCAL WDG module shall support MCU2_1 core of SoC | Verify WDG functionality on MCU2_1 core of SoC works as expected without errors. | EVM Verification | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
73 | MCAL-3037 | 6008 | Qualification | MCAL-5549 | WDG Module Common: The MCAL modules shall be unit tested using test suite written in compliance with a common unit test framework.The test suite can be automated and used for both functional (black box testing) and unit level test (white box testing) | Check for the UT log and ensure a menu is presented and test stats are printed. | Review | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
74 | MCAL-3039 | 6009 | Qualification | MCAL-5549 | WDG Module Common: The MCAL shall provide test report for each MCAL module | Check for presence of module test report in RC / Final package | Review | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional
75 | MCAL-3048 | 6010 | Qualification | MCAL-5549 | WDG Module Common: MCAL modules shall follow guidelines provided by MISRA C 2012, third party tool (such as KLOCKWORK) shall be used to ensure compliance.MCAL release shall include MISRA C report & MISRA C Policy | Ensure KLOCKWROK / MISRAC report is included in RC under docs folder. | Review | P0 | PASS | √ | √ |  |  | Requirements Analysis | usability
76 | MCAL-3028 | 6011 | Qualification | MCAL-5628 | WDG Module Common: Is the example BFT run on EVM | WDG should be serviced by the driver with set trigger condition(until trigger counter = 0) and then it should generate an interrupt to ESM after expiry. Confirm interrupt generated to ESM is from WDG only. | EVM Verification | P0 | PASS | √ | √ |  |  | Requirements Analysis | Functional

## Revision History
Document Revision History (Template Version 2.00)
S.No | Author | Version | Date | Approval | Description
1 | Raja Kumar | 0.1 | 2022-12-15 | Approved | Wdg Initial test plan
2 | Raja Kumar | 0.2 | 2023-03-06 | Approved | Updated Test Cases, Release and Baseline Version.

## Help
Test State | Description | State
Not Run | Test Not Run Yet | NRY
Pass | Test Pass | PASS
Fail | Test Fail | FAIL
Blocked | Test Blocked because of other test case failure or an Open MR from previous Release | BLK
Not Implemented | Test Not Supported by this release as the feature is not implemented | NI
Not Applicable | Test can not be run because of Hardware is not available on the platform or Hardware does not support this feature. | NA
Not Required | Test is not required to run for this release | NRQ
Test Category | Description
Sanity | Test Summary: Only Sanity Checks have been run on the release Test Case: This Test is identified to run for Sanity Checks
Regression | Test Summary: Only Regression was completed on the release Test Case: This Test is identified to run for Regression
Full | Test Summary: All Tests have been run Test Case: This Test is identified to run in a full cycle
Test Automation | Description
Completed | Test Case has been automated. The Filename field cannot be empty if the test is automated
Planned | Test Case automation has been planned but not yet completed
Not Scoped | Test Case cannot be automated or not planned.
Test Adequacy | Description
Functional | Test Case covers functional aspects of the module
Usability | Test Case covers usability/api/look and feel aspects of the module Cover DSP/LINK Scalability tests under this.
Performance | Test Case covers performance, profiling, latency etc. Audio Quality and Video Quality tests will be covered here IEEE Defn: To determine if the software can handle the anticipated amount of work in the required time
Reliability | Test Case ensures that the component does not fail over time IEEE Defn: The ability of a system or component to perform its required functions under stated conditions for a specified period of tim
Stress | Test Case checks for API stability, load/unload of modules, create/delete, stress under different load conditions etc. IEEE Defn: To determine if the software can handle an unanticipated amount of work
Negative | Test Case covers error/negative aspects of the module
Equivalence | Test case that groups the test item into classes where all items in each class are suppose to behave exactly the same. The theory is that need to test one of each item to make sure the system works.
Verification | Requirements Needs to be verified Manually
Configurator | Configuration specific test
Test Coverage | Description
Base RTOS | This requirement is covered as part of the base operating system usage.
Out of Test Scope | This requirement cannot be tested by System Test
No Testing Required | This requirement does not require any testing
Test Definition Pending | Test Definition for this requirement is pending
Pre Silicon Scope | Description
Yes | Test Case can be run in both Pre Silicon and Post Silicon Platforms
No | Test Case can be run only on Post Silicon Platform
Pre BFT | Description
Yes | This test needs to be run by Development team before release to System Test. This is part of the input criteria
No | This Test need not be run by the development team before releasing to System Test
Test Summary | Description
Release | The release number
Platform | The platform or board on which the tests were run
Tester Name | Name of the tester
Scope | Scope can be Sanity, Regression or Full
History | Description
- | If it is the initial draft then the document has not yet been approved.
PDS | Version of the document signed off on PDS
Project Manager | Versions subsequent to PDS sign off, that are approved by the TI Project Manager.
Requirements Coverage | Description
Requirement xxx | Map all tests to this requirement. Make sure that the Testing Scope in the summary is also filled up. Map the RDD URL to this location in the summary sheet
System | Map tests that are derived from protocol, hardware or IP but do not have a specific software requirement as system
Test Setup | Description
Setup xxx | Describe the test setup for the test case